## WS1
Project | End Date | Lane | Total Points | In Work | Assigned to
Taskmaster Disaggregation | None | Approved | 0 | 0 | Daniel Gonzalez
Artifactory Production Upgrade & Resource Tuning | None | Approved | 4 | 4 | Wade Naveja, Guillaume THOMAS
Artifactory HTTPS Support | None | Approved | 0 | 0 | Wade Naveja, Guillaume THOMAS
OneFS Simulator Test automation | None | Approved | 0 | 0 | Rick Ludvigsen, Guillaume THOMAS
Convert existing CC scripts to Python | None | Approved | 0 | 0 | Ananthan Pillai
Quarantine Nag Mail for Leads | None | Approved | 0 | 0 | Guillaume THOMAS
Wiki Salt automation and version upgrade | None | Approved | 0 | 0 | Guillaume THOMAS, Xuan Du
PXE Firmware upgrade via Taskmaster | None | Approved | 0 | 0 | Daniel Gonzalez
PXE firmware upgrade support | None | Approved | 0 | 0 | Daniel Gonzalez
Mandatory Test List Timeouts | None | Approved | 0 | 0 | Daniel Gonzalez
Duct Tape client provisioning | None | Discarded or Obsolete | 0 | 0 | Daniel Gonzalez, Tucker Siemens
Github Enterprise Appliance Upgrade | 2018-03-09 | Finished As Planned | 3 | 3 | Wade Naveja, Guillaume THOMAS
save_logs deployment | 2018-03-02 | Finished As Planned | 13 | 13 | Daniel Gonzalez, Alba Magallanes
Ice Age Integration | None | Finished As Planned | 1 | 1 | Daniel Gonzalez, Alba Magallanes
Icarus Backports | 2018-02-23 | Finished As Planned | 13 | 13 | Daniel Gonzalez, Stuart Higgins
Lazarus | None | Finished As Planned | 8 | 8 | Evan Cramer, Daniel Gonzalez
v4.1 live ongoing | 2018-03-15 | Finished As Planned | 17 | 17 | Chris Tabor, Guillaume THOMAS
Coverity Low on Disk Space - 96% - Critical Bug | None | Finished As Planned | 0 | 0 | Rick Ludvigsen, Guillaume THOMAS
Dell Lab Standard and Safety Training | None | Finished As Planned | 0 | 0 | Richard Blalock
[Opengrok] OpengrokVM Scripting and Deploy | 2018-03-05 | Finished As Planned | 6 | 6 | Xuan Du, Jimmy Sun, Tom Liu
Regression Wheel Firmware upgrade | None | Finished As Planned | 5 | 5 | Jimmy Sun, Tom Liu
Relocate SSDs from Build hosts to T1 Cluster | None | Finished As Planned | 3 | 3 | Daniel Mills, Guillaume THOMAS
Deployment of Build Artifact Changes for Bug 196150 | None | Finished As Planned | 1 | 1 | Rick Ludvigsen, Guillaume THOMAS
Deployment of Build Executor Version 258 | None | Finished As Planned | 2 | 2 | Rick Ludvigsen, Guillaume THOMAS
RW H/W Swap & CAPEX (trading with compression team) | 2018-02-09 | Finished As Planned | 2 | 2 | Guillaume THOMAS
Incremental Build Support - DUPLICATE | None | Finished As Planned | 0 | 0 | Guillaume THOMAS
Train Jimmy, Tom, Bill, & Mark | None | Finished As Planned | 3 | 3
Review Board Upgrade | 2018-02-02 | Finished As Planned | 0 | 0 | Vince Thyng, Guillaume THOMAS
Code Coverage :Dev & TestMgr Workflow | None | Finished As Planned | 0 | 0 | Ananthan Pillai
RW – Shanghai Onboarding | 2018-02-16 | Finished As Planned | 0 | 0 | Guillaume THOMAS
CC for Python bindings | None | Finished As Planned | 0 | 0 | Ananthan Pillai
Code Coverage in Regression Wheel | None | Finished As Planned | 0 | 0 | Ananthan Pillai
Code Coverage for Niijima Builds | None | Finished As Planned | 0 | 0 | Ananthan Pillai
Elastic (ELK) Log Stack | None | Finished As Planned | 0 | 0
Legacy Firmware Updates | None | Finished As Planned | 0 | 0
Versioned patch data project | None | In Design | 2 | 2 | Chris Tabor, Guillaume THOMAS
Migrate GHAPR to Centralized Hosting | None | In Design | 4 | 4 | Vince Thyng, Guillaume THOMAS
PaaS Tier 1 | None | In Design | 4 | 4 | Vince Thyng, Guillaume THOMAS
Parser toolkit project | None | In Progress | 53 | 32 | Ganesh Prabhu, Guillaume THOMAS
vSphere 6.5 Upgrade | 2018-05-31 | In Progress | 10 | 10 | Daniel Mills, Guillaume THOMAS
Code Coverage for Statview | 2018-03-30 | In Progress | 6 | 3 | Ananthan Pillai
Release Code Signing | None | In Progress | 9 | 3 | Robert Haddon, Guillaume THOMAS
Wiki Merge & Puppetize | 2018-03-23 | In Progress | 22 | 12 | Robert Haddon, Guillaume THOMAS
Seattle Distribution Switch Overhaul | 2018-03-30 | In Progress | 28 | 19 | Ananthan Pillai, Phong Truong
ImageMaker Integration | None | In Progress | 0 | 0 | Robert Haddon, Guillaume THOMAS
Static Analysis for Spectre and Meltdown | 2018-03-23 | In Progress | 13 | 12 | Rick Ludvigsen, Guillaume THOMAS
Research and deploy production ESRS gateway | None | In Progress | 0 | 0 | Richard Blalock, Guillaume THOMAS
BugReports onboarding and Dell R-DMetrics | 2018-03-12 | In Progress | 22 | 22 | Brooks Kindle, Guillaume THOMAS
GCP (TEaaS) - M3 | 2018-03-31 | In Progress | 142 | 106 | Daniel Gonzalez
Metadata | None | In Progress | 52 | 8 | Greg Bristol, Daniel Gonzalez
Code Coverage for Pipeline Builds | 2018-03-30 | In Progress | 58 | 58 | Ananthan Pillai
DataIQ Mainteanance | None | In Progress | 22 | 13 | Guillaume THOMAS
IPv6 Testing in Durham | 2018-04-30 | In Progress | 19 | 11 | Phong Truong, Guillaume THOMAS
[vROPs] Seattle and Durham setup | 2018-03-30 | In Progress | 19 | 5 | Xuan Du, Jimmy Sun, Tom Liu
Automated Test Scheduler Rework | 2018-03-14 | In Progress | 6 | 6 | Daniel Gonzalez, Alba Magallanes
Host Packet Capture Analyzer tool on Eng Inf | 2018-03-31 | In Progress | 0 | 0 | Ganesh Prabhu, Guillaume THOMAS
DataIQ 1.5 | 2018-03-09 | In Progress | 6 | 6 | Ethan Madden, Guillaume THOMAS
Code Coverage : Improvements for isi_coverage.sh | 2018-03-30 | In Progress | 10 | 10 | Ananthan Pillai
Artifactory Dev & Stage Environment Refresh | 2018-03-23 | In Progress | 4 | 4 | Wade Naveja, Guillaume THOMAS
Artifactory rpm repo archiving plug-in install & configuration | None | In Progress | 2 | 1 | Wade Naveja, Guillaume THOMAS
GCP (TEaaS) - M4 | 2018-06-29 | In Progress | 28 | 17 | Daniel Gonzalez
Leankit integration & reporting | None | In Progress | 0 | 0 | Guillaume THOMAS
Project status reporting (web server) | None | In Progress | 4 | 4 | Guillaume THOMAS
Reduce time to market | None | New Requests | 0 | 0 | Greg Bristol, Daniel Gonzalez
scripts management going forward | None | New Requests | 0 | 0 | Chris Tabor, Guillaume THOMAS
PXE Taskmaster Integration | None | New Requests | 4 | 0 | Dan Forrest
Code Coverage Resource Utilization on RW | None | New Requests | 0 | 0 | Ananthan Pillai
Comprehensive DEBUG patch handling | None | New Requests | 0 | 0 | Chris Tabor, Guillaume THOMAS
Code Coverage weekly report | None | New Requests | 0 | 0 | Ananthan Pillai
Code Coverage for NJ | None | New Requests | 0 | 0 | Ananthan Pillai
Bug reports for MRs | None | New Requests | 0 | 0 | Chris Tabor, Guillaume THOMAS
Code Coverage : Incorporate WebUI CC | None | New Requests | 0 | 0 | Ananthan Pillai
Code Coverage : Root Partition issue on vOneFS | None | New Requests | 0 | 0 | Ananthan Pillai
Code Coverage: NDU | None | New Requests | 0 | 0 | Ananthan Pillai
Composable Release Support | None | New Requests | 0 | 0
Formal mapping of ignored files for correlation | None | New Requests | 0 | 0 | Chris Tabor, Guillaume THOMAS
Functional script verification & testing integration | None | New Requests | 0 | 0 | Chris Tabor, Guillaume THOMAS
Replace and decommission patch upload | None | New Requests | 0 | 0 | Chris Tabor, Guillaume THOMAS
Reviewboard ship-it verification & auto-updates | None | New Requests | 0 | 0 | Chris Tabor, Guillaume THOMAS
Removal of XML preview/usage from spog and inputs | None | New Requests | 0 | 0 | Chris Tabor, Guillaume THOMAS
Ability to pre-install matching customer patches on cluster pre-mechanics testing | None | New Requests | 0 | 0 | Chris Tabor, Guillaume THOMAS
DR & Backup for Eng Inf | None | Scoping | 4 | 4 | Richard Blalock, Guillaume THOMAS
Research and Deploy Superna Eyeglass for cluster config backup | None | Scoping | 0 | 0 | Richard Blalock
Upgrade/rollback automation for patches | None | Scoping | 1 | 1 | Chris Tabor, Guillaume THOMAS
InsightIQ Upgrade | None | Scoping | 0 | 0 | Richard Blalock
Data Retention | None | Scoping | 0 | 0 | Richard Blalock
OneFS Upgrade cadence | None | Scoping | 0 | 0 | Richard Blalock
Research and Facilitate OneFS GS training | None | Scoping | 0 | 0 | Richard Blalock
Improve GitHub performance for Shanghai/India | None | Scoping | 9 | 6 | Phong Truong, Guillaume THOMAS
Cluster monitoring automation | None | Scoping | 2 | 2 | Vince Thyng, Guillaume THOMAS
OneFS SysAdmin Training | None | Scoping | 0 | 0 | Richard Blalock, Guillaume THOMAS
Centralized Database | None | Scoping | 0 | 0 | Reilly Steele, Daniel Gonzalez
RevBot Mail Improvements | None | Scoping | 14 | 6 | Dan Forrest, Daniel Gonzalez
CloudIQ | None | Scoping | 22 | 19 | Shaun Edwards, Daniel Gonzalez
ServiceNow / Taskmaster Integration | None | Scoping | 20 | 20 | Daniel Gonzalez, Stuart Higgins
Pull Request Automation and Management Tools | None | Scoping | 1 | 0 | Brooks Kindle, Guillaume THOMAS
Formalize Isilon-CEE infrastructure and decide on config management schema, if any | None | Scoping | 0 | 0 | Jesse Rhodes, Guillaume THOMAS
Replace existing version of Puppet with SALT M1 | None | Scoping | 3 | 3 | Ethan Madden, Guillaume THOMAS
MR Branch & Release Automation | None | Scoping | 2 | 2 | Rick Ludvigsen, Guillaume THOMAS
Evaluate vRealize Automation for internal cloud use | None | Scoping | 3 | 3 | Daniel Mills, Guillaume THOMAS
Artifactory Tier 1 SLA Compliance-Reqs & analysis | None | Scoping | 0 | 0 | Wade Naveja, Guillaume THOMAS
Corruption Tool | None | Scoping | 1 | 1 | Brooks Kindle, Guillaume THOMAS
Jenkins Upgrade | None | Scoping | 10 | 10 | Rick Ludvigsen, Guillaume THOMAS
Code Coverage for normal Python code in OneFS | None | Scoping | 20 | 17 | Ananthan Pillai
VCenter Harmonization, Modernization and Expansion | None | Scoping | 2 | 2 | Daniel Mills, Guillaume THOMAS
Automated Patches M3 | None | Under Review | 0 | 0