## Projects_list
DR & Backup for Eng Inf
Research and Deploy Superna Eyeglass for cluster config backup
Parser toolkit project
Versioned patch data project
Upgrade/rollback automation for patches
InsightIQ Upgrade
Github Enterprise Appliance Upgrade
Data Retention
OneFS Upgrade cadence
Research and Facilitate OneFS GS training
vSphere 6.5 Upgrade
Code Coverage for Statview
save_logs deployment
Ice Age Integration
Icarus Backports
Lazarus
v4.1 live ongoing
Improve GitHub performance for Shanghai/India
Release Code Signing
Wiki Merge & Puppetize
Seattle Distribution Switch Overhaul
ImageMaker Integration
Migrate GHAPR to Centralized Hosting
PaaS Tier 1
Cluster monitoring automation
Coverity Low on Disk Space - 96% - Critical Bug
Static Analysis for Spectre and Meltdown
Dell Lab Standard and Safety Training
Research and deploy production ESRS gateway
OneFS SysAdmin Training
Reduce time to market
Taskmaster Disaggregation
Centralized Database
RevBot Mail Improvements
BugReports onboarding and Dell R-DMetrics
GCP (TEaaS) - M3
Metadata
Code Coverage for Pipeline Builds
scripts management going forward
DataIQ Mainteanance
CloudIQ
ServiceNow / Taskmaster Integration
IPv6 Testing in Durham
[Opengrok] OpengrokVM Scripting and Deploy
Regression Wheel Firmware upgrade
[vROPs] Seattle and Durham setup
Pull Request Automation and Management Tools
Automated Test Scheduler Rework
PXE Taskmaster Integration
Formalize Isilon-CEE infrastructure and decide on config management schema, if any
Host Packet Capture Analyzer tool on Eng Inf
Replace existing version of Puppet with SALT M1
DataIQ 1.5
Code Coverage : Improvements for isi_coverage.sh
MR Branch & Release Automation
Evaluate vRealize Automation for internal cloud use
Artifactory Production Upgrade & Resource Tuning
Artifactory HTTPS Support
Artifactory Tier 1 SLA Compliance-Reqs & analysis
Artifactory Dev & Stage Environment Refresh
Artifactory rpm repo archiving plug-in install & configuration
Relocate SSDs from Build hosts to T1 Cluster
Deployment of Build Artifact Changes for Bug 196150
Deployment of Build Executor Version 258
RW H/W Swap & CAPEX (trading with compression team)
Incremental Build Support - DUPLICATE
Code Coverage Resource Utilization on RW
Corruption Tool
Comprehensive DEBUG patch handling
Jenkins Upgrade
GCP (TEaaS) - M4
Train Jimmy, Tom, Bill, & Mark
Leankit integration & reporting
Code Coverage for normal Python code in OneFS
OneFS Simulator Test automation
Project status reporting (web server)
VCenter Harmonization, Modernization and Expansion
Convert existing CC scripts to Python
Review Board Upgrade
Code Coverage weekly report
Code Coverage for NJ
Bug reports for MRs
Code Coverage : Incorporate WebUI CC
Code Coverage : Root Partition issue on vOneFS
Code Coverage: NDU
Automated Patches M3
Quarantine Nag Mail for Leads
Wiki Salt automation and version upgrade
Composable Release Support
Code Coverage :Dev & TestMgr Workflow
Formal mapping of ignored files for correlation
Functional script verification & testing integration
Replace and decommission patch upload
Reviewboard ship-it verification & auto-updates
Removal of XML preview/usage from spog and inputs
Ability to pre-install matching customer patches on cluster pre-mechanics testing
RW – Shanghai Onboarding
CC for Python bindings
Code Coverage in Regression Wheel
Code Coverage for Niijima Builds
PXE Firmware upgrade via Taskmaster
PXE firmware upgrade support
Duct Tape client provisioning
Mandatory Test List Timeouts
Elastic (ELK) Log Stack
Legacy Firmware Updates

## DR & Backup for Eng Inf
DR & Backup for Eng Inf
normal | Task | Github Restore Firedrill | 1 | Doing Now | Wade Naveja
normal | Task | DR Whitepaper research | 2 | Finished As Planned | Wade Naveja
normal | Task | Backup/Restore utility research | 1 | Finished As Planned | Wade Naveja
high | Epic | SyncIQ Policy Review and Remediation | 0 | Next Sprint Planning | Richard Blalock

## Research and Deploy Superna Eye
Research and Deploy Superna Eyeglass for cluster config backup

## Parser toolkit project
Parser toolkit project
normal | Task | Add a syslog filter to filter based on appName value | 2 | Under Review | Ganesh Prabhu
normal | Task | Fix patch_list parser with new version of patch name and new error message. | 1 | Finished As Planned | Edward Hodapp
high | Task | Create parser for etcifs.tar/ifs/firmware_versions files. | 3 | Next Sprint Planning | Edward Hodapp
normal | Task | Create table parser output wrapper | 3 | Doing Now | Edward Hodapp
normal | Task | Investigate root cause of failures of the licenses parser. | 3 | Finished As Planned | Edward Hodapp
normal | Task | Add string match/ regex match for the filtered messages | 3 | Next Sprint Planning | Ganesh Prabhu
high | Task | Create parser for isi_event files | 3 | Current Sprint Backlog | Edward Hodapp
normal | Task | Investigate root cause of failures of get_cluster_avscan parser. | 3 | Backlog | Edward Hodapp
normal | Task | syslog parser unit test | 1 | Finished As Planned | Ganesh Prabhu
normal | Task | Write PSA for panic parser | 2 | Current Sprint Backlog | Ganesh Prabhu
normal | Task | Learn about regen tests for parsers, filters. Write regen test for the corruption filter | 3 | Backlog | Ganesh Prabhu
normal | Task | Write a parser filter to filter out corruption messages from syslog and run it on sample log files | 3 | Finished As Planned | Ganesh Prabhu
normal | Task | parse_hw_status is failing on new messages that have appeared. Fix it. | 3 | Finished As Planned | Edward Hodapp
normal | Task | Investigate root cause of parse_node_radish failures. | 1 | Finished As Planned | Edward Hodapp
high | Task | patch_list parser: remove node list from patch sha256 hash. | 3 | Finished As Planned | Edward Hodapp
normal | Task | Remove Status from patch sha256 in patch_list parser. | 1 | Finished As Planned | Edward Hodapp
normal | Task | Write unit tests for syslog filter. | 2 | Finished As Planned | Ganesh Prabhu, Guillaume THOMAS
normal | Task | Investigate building detailed drive model data model. | 3 | Finished As Planned | Ethan Madden, Edward Hodapp
normal | Task | Investigate root cause of failures of SMB parsers. | 3 | Next Sprint Planning | Edward Hodapp
normal | Task | Investigate root cause for nfs_exports parsers failures. | 3 | Next Sprint Planning | Edward Hodapp
normal | Task | Investigate the root cause of gconfig parser failures. | 3 | Next Sprint Planning | Edward Hodapp
normal | Task | Set up environment, install parser toolkit, understand use cases etc. | 1 | Finished As Planned | Ganesh Prabhu
normal | Epic | Process Adhoc requests | 0 | Backlog | Ganesh Prabhu
normal | Epic | Write a toolchain and a database modification (details unknown as of now) | 0 | Backlog | Ganesh Prabhu

## Versioned patch data project
Versioned patch data project
normal | Task | Write PSA | 2 | Under Review | Chris Tabor

## Upgrade rollback automation for
Upgrade/rollback automation for patches
normal | Task | Finish review of PSA and begin planning | 1 | Under Review | Chris Tabor

## InsightIQ Upgrade
InsightIQ Upgrade

## Github Enterprise Appliance Upg
Github Enterprise Appliance Upgrade
normal | Task | GHE Dev Appliance Upgrade | 1 | Finished As Planned | Wade Naveja
normal | Task | GHE Prod Appliance Upgrade - Prod Outage | 2 | Finished As Planned | Wade Naveja

## Data Retention
Data Retention

## OneFS Upgrade cadence
OneFS Upgrade cadence

## Research and Facilitate OneFS G
Research and Facilitate OneFS GS training

## vSphere 6.5 Upgrade
vSphere 6.5 Upgrade
normal | Task | Test Duct Tape Prior to upgrade | 1 | Doing Now | Daniel Mills
normal | Task | Deploy vCenter Certificates | 1 | Finished As Planned | Daniel Mills
normal | Task | Upgrade vCenter | 1 | Current Sprint Backlog | Daniel Mills
normal | Task | Test Duct Tape post upgrade | 1 | Current Sprint Backlog | Daniel Mills
normal | Task | Upgrade ESXi | 1 | Current Sprint Backlog | Daniel Mills
normal | Task | Upgrade PSCs | 1 | Current Sprint Backlog | Daniel Mills
normal | Task | Update and promote test DCs | 1 | Finished As Planned | Daniel Mills
normal | Task | Connect vSphere Test to AD | 1 | Finished As Planned | Daniel Mills
normal | Task | Configure vSphere Test environment | 2 | Finished As Planned | Daniel Mills

## Code Coverage for Statview
Code Coverage for Statview
normal | Task | Statview wiki documentation | 3 | Next Sprint Planning | dharmender jain
normal | Task | Write a separate script for Statview | 3 | Under Review | dharmender jain
normal | Task | Provide a patch to Harish to instrument and generate statview coverage | 0 | Finished As Planned | dharmender jain

## save_logs deployment
save_logs deployment
normal | Task | Deploy save_logs enhancements | 1 | Finished As Planned | Alba Magallanes
normal | Task | Code review the save_logs changes | 2 | Finished As Planned | Alba Magallanes
normal | Task | save_logs visible way of let users know the unfurl status. | 1 | Finished As Planned | Alba Magallanes
normal | Task | Improve status of unfurl | 2 | Finished As Planned | Alba Magallanes
normal | Task | save_logs statistics doc | 2 | Finished As Planned | Alba Magallanes
normal | Task | Run save_logs tests with new branches. | 3 | Finished As Planned | Alba Magallanes
normal | Task | Let QA Management know about the new save_logs process | 2 | Finished As Planned | Daniel Gonzalez, Alba Magallanes

## Ice Age Integration
Ice Age Integration
normal | Task | Iceage prod deployment | 1 | Finished As Planned | Alba Magallanes

## Icarus Backports
Icarus Backports
normal | Task | Create PR for 8.1.0.3 Icarus backport | 1 | Finished As Planned | Stuart Higgins
normal | Task | Backport Icarus to 8.1.1.2 | 1 | Finished As Planned | Stuart Higgins
normal | Task | Test and debug 8.1.1.2 Icarus backport | 3 | Finished As Planned | Stuart Higgins
normal | Task | Create PR for 8.1.1.2 Icarus backport | 1 | Finished As Planned | Stuart Higgins
normal | Task | Testing/bugfix 8.1.0.3 Icarus backport | 3 | Finished As Planned | Stuart Higgins
normal | Task | Create PR for Icarus merge to 8.0.0.7 | 3 | Finished As Planned | Stuart Higgins
normal | Task | Merge Icarus changes into 8.1.0.3 private branch | 1 | Finished As Planned | Stuart Higgins

## Lazarus
Lazarus
normal | Task | Bug 215217 (the lazarus issue that platform team reported) | 5 | Finished As Planned | Evan Cramer
normal | Task | Add Lazarus Gen6 Support | 3 | Finished As Planned | Evan Cramer

## v4.1 live ongoing
v4.1 live ongoing
normal | Task | investigate correlation issues for security RUPs, use to test CHMOD correlation changes | 2 | Finished As Planned | Chris Tabor
normal | Task | get workflow_tools code coverage from 50% to 60% | 1 | Finished As Planned | Chris Tabor
normal | Task | Add ability in spog to choose services via a table | 1 | Finished As Planned | Chris Tabor
normal | Task | Use procstat method for pid verification | 1 | Finished As Planned | Chris Tabor
normal | Task | Shadow Blong for patch 218955 | 2 | Finished As Planned | Chris Tabor
normal | Task | Add and test option for using both mcp and procstat pid verification methods | 2 | Finished As Planned | Chris Tabor
normal | Task | Add security specific chmod changes for binary correlation | 2 | Finished As Planned | Chris Tabor
normal | Task | spog UI issues from shadowing Blong | 1 | Finished As Planned | Chris Tabor
normal | Task | PID verification failure for isi_avscan | 1 | Finished As Planned | Chris Tabor
normal | Task | svclist xml error for 8.1.0.x | 1 | Finished As Planned | Chris Tabor
normal | Task | Manually backfille archived patches into spog db to mitigate false negatives in patches | 0 | Finished As Planned | Chris Tabor
normal | Task | Check for inconsistent service names and add wrapper pid getter for each. | 0 | Finished As Planned | Chris Tabor
normal | Task | Look into more robust handling of patch service detection | 1 | Finished As Planned | Chris Tabor
normal | Task | Debugging issues with patch install 216929 | 0 | Finished As Planned | Chris Tabor
normal | Task | Check for core dumps on all nodes | 0 | Finished As Planned | Chris Tabor
normal | Task | Look into PAPI REST error / isi_papi_d restarts | 1 | Finished As Planned | Chris Tabor
normal | Task | Create FAQs/tips/usage wiki page for users | 0 | Finished As Planned | Chris Tabor
normal | Task | PID verification failure for HDFS | 1 | Finished As Planned | Chris Tabor
normal | Task | analyze failed logs to determine failure categories | 0 | Finished As Planned | Chris Tabor
normal | Task | Determine a better service detection strategy with patch group | 0 | Finished As Planned | Chris Tabor
normal | Task | Remove conflicts/deprecations list from pkgcomment | 0 | Finished As Planned | Chris Tabor
normal | Task | Look into how to handle manual modification of kernel patches where kernel.gz is ignored in correlation | 0 | Finished As Planned | Chris Tabor
normal | Task | Fix plist not getting updated when using legacy_files in correlation job to override kernel file | 0 | Finished As Planned | Chris Tabor
normal | Task | no_scripts flag not working for job | 0 | Finished As Planned | Chris Tabor
normal | Task | Commit listing UI/auto-commit gathering | 0 | Finished As Planned | Chris Tabor, Guillaume THOMAS

## Improve GitHub performance for
Improve GitHub performance for Shanghai/India
normal | Task | Explore using IEO's shared GitHub instance | 4 | Doing Now | Phong Truong
normal | Task | Follow up with IT | 1 | Finished As Planned | Phong Truong
normal | Task | Schedule a call with GitHub | 1 | Finished As Planned | Phong Truong
normal | Task | GitHub: Document workflow and performance with Shanghai team | 3 | Backlog | Phong Truong

## Release Code Signing
Release Code Signing
normal | Task | Signing with Sign OVA | 3 | Backlog | Robert Haddon
normal | Task | Choose CSP | 3 | Backlog | Robert Haddon
normal | Task | Code Signing manifest format paper | 1 | Finished As Planned | Robert Haddon
normal | Task | Decide on manifest format | 1 | Current Sprint Backlog | Robert Haddon
normal | Task | Write PSA | 1 | Under Review | Robert Haddon

## Wiki Merge & Puppetize
Wiki Merge & Puppetize
normal | Task | Configure Nginx for wiki with Puppet | 3 | Finished As Planned | Jesse Rhodes
normal | Task | Configure PHP for wiki with Puppet | 3 | Finished As Planned | Jesse Rhodes
normal | Task | Document Wiki merge/upgrade process | 3 | Under Review | Robert Haddon
normal | Task | Write recommended approach to merge LWwiki and Isipedia | 2 | Under Review | Robert Haddon
normal | Task | Build Restore Process | 1 | Finished As Planned | Robert Haddon
normal | Epic | Massage Obsolete Extensions | 10 | Backlog | Robert Haddon

## Seattle Distribution Switch Ove
Seattle Distribution Switch Overhaul
normal | Task | Configure new 7010-T 1-gig switches | 3 | Under Review | Phong Truong
normal | Task | Run new patch panels for 10-gig uplinks | 5 | Next Sprint Planning | Phong Truong
normal | Task | SDSO: Configure Nexus 5K distribution switches | 4 | Finished As Planned | Phong Truong
normal | Task | Cutover to new switches - one switch or row at a time | 8 | Current Sprint Backlog | Phong Truong
normal | Task | Upgrade and configure replacement Arista 7010/7048 switches | 3 | Under Review | Phong Truong
normal | Task | Procure cables, patch panels, and SFPs | 1 | Current Sprint Backlog | Phong Truong
normal | Task | Decommission old 1gig switches | 3 | Next Sprint Planning | Phong Truong
normal | Task | Add new switches to Zabbix/Netbrain monitoring | 1 | Next Sprint Planning | Phong Truong

## ImageMaker Integration
ImageMaker Integration

## Migrate GHAPR to Centralized Ho
Migrate GHAPR to Centralized Hosting
normal | Task | Write PSA | 2 | Finished As Planned | Vince Thyng
normal | Task | GHAPR Design document | 2 | Doing Now | Vince Thyng

## PaaS Tier 1
PaaS Tier 1
normal | Task | PaaS Tier 1 Design Documentation | 1 | Under Review | Vince Thyng
normal | Task | Write PSA | 3 | Finished As Planned | Vince Thyng

## Cluster monitoring automation
Cluster monitoring automation
normal | Task | Discuss with Ethan, Paul Croft abt Richard's dashboard replacement | 2 | Doing Now | Vince Thyng

## Coverity Low on Disk Space - 96
Coverity Low on Disk Space - 96% - Critical Bug

## Static Analysis for Spectre and
Static Analysis for Spectre and Meltdown
normal | Task | Run the Spectre analysis tool on the FreeBSD12 build | 1 | Backlog | Rick Ludvigsen
normal | Task | Spectre Analysis for FreeBSD Head - 3 | 2 | Finished As Planned | Rick Ludvigsen
normal | Task | Spectre Analysis for FreeBSD Head - 2 | 3 | Finished As Planned | Rick Ludvigsen
normal | Task | Spectre Analysis for FreeBSD Head - 4 | 2 | Doing Now | Rick Ludvigsen
normal | Task | Spectre Analysis for FreeBSD Head - 1 | 3 | Finished As Planned | Rick Ludvigsen
normal | Task | Spectre Analysis for 7.X | 2 | Finished As Planned | Rick Ludvigsen

## Dell Lab Standard and Safety Tr
Dell Lab Standard and Safety Training
normal | Task | Take Tech2045 Course | 0 | Finished As Planned | Richard Blalock

## Research and deploy production
Research and deploy production ESRS gateway
high | Task | Download and deploy new instance of ESRS version 3.26. | 0 | Doing Now | Richard Blalock
normal | Task | Send Serial Number list to ESRS Dev Team | 0 | Finished As Planned | Richard Blalock
high | Task | Open RAMP request for new VM | 0 | Finished As Planned | Richard Blalock
high | Task | Decommission / Destroy Current POC VM of ESRS. | 0 | Finished As Planned | Richard Blalock
normal | Task | Adding Primary ESRS Cluster to Production Clusters | 0 | Next Sprint Planning | Richard Blalock

## OneFS SysAdmin Training
OneFS SysAdmin Training

## Reduce time to market
Reduce time to market

## Taskmaster Disaggregation
Taskmaster Disaggregation

## Centralized Database
Centralized Database

## RevBot Mail Improvements
RevBot Mail Improvements
normal | Task | Move RevBot code location and update server cron jobs. | 1 | Backlog | Dan Forrest
normal | Task | Update RevBot e-mail notifications | 2 | Backlog | Dan Forrest
normal | Task | Update RevBot UI | 2 | Backlog | Dan Forrest
normal | Task | Update RevBot code to point to github instead of svn. | 3 | Backlog | Dan Forrest
normal | Task | Write PSA for migrating RevBot to git. | 3 | Under Review | Dan Forrest
normal | Task | Investigate moving RevBot from SVN to Git | 3 | Finished As Planned | Dan Forrest

## BugReports onboarding and Dell
BugReports onboarding and Dell R-DMetrics
normal | Task | Backport R&D metrics to releases-scope | 1 | Finished As Planned | Brooks Kindle
normal | Task | Backport R&D metrics to releases-implementation | 3 | Finished As Planned | Brooks Kindle
normal | Task | Find and fix issue with BugReports' Totals column | 3 | Finished As Planned | Brooks Kindle
normal | Task | Replace daily dell-r-dmetrics view with a weekly view | 3 | Current Sprint Backlog | Brooks Kindle
normal | Task | Fix TCum: Weekly and TCum: All columns in bugreports | 3 | Current Sprint Backlog | Brooks Kindle
normal | Task | Fix Net Open column in bugreports | 3 | Doing Now | Brooks Kindle
normal | Task | Figure out how to fix the Dell r-dmetrics bug counts issue | 3 | Finished As Planned | Brooks Kindle
normal | Task | Onboard myself for the BugReports project | 3 | Finished As Planned | Brooks Kindle
normal | Task | Bugreports refactor branch fix | 0 | Finished As Planned | Chris Tabor

## GCP (TEaaS) - M3
GCP (TEaaS) - M3
normal | Task | Update puppet with RDU values | 1 | Current Sprint Backlog | Reilly Steele
normal | Task | Create ducttape staging rdu worker | 2 | Doing Now | Reilly Steele
normal | Task | Create PSA for ducttape continuous testing / monitoring | 1 | Doing Now | Reilly Steele
normal | Task | Update/Add ducttape (vCenter) system tests | 3 | Under Review | Reilly Steele
normal | Task | Add ducttape (gcp) system tests | 3 | Under Review | Reilly Steele
normal | Task | Determine ducttape API v1.0 -> API v2.0 migration strategy | 1 | Finished As Planned | Reilly Steele, Tucker Siemens
normal | Task | Revisit/Evaluate ACS and vOneFS machine.id bugs | 1 | Finished As Planned | Tucker Siemens
normal | Task | Buildweb GCP Beta edit current polling functions to exclude GCP resources | 3 | Finished As Planned | Forest Clay
normal | Task | Buildweb GCP Beta write unit tests | 2 | Finished As Planned | Forest Clay
normal | Task | Test ducttape location functionality for vsphere vclusters | 2 | Finished As Planned | Reilly Steele
normal | Task | Create database migration to ducttape 2.0 schema | 2 | Finished As Planned | Reilly Steele
normal | Task | Test combining seattle and durham databases | 2 | Finished As Planned | Reilly Steele
normal | Task | Merge ducttape gcp branches to master | 1 | Finished As Planned | Reilly Steele
normal | Task | Respond to ACS/vOneFS machine.id reviews | 2 | Finished As Planned | Tucker Siemens
normal | Task | Assist Evan with Image maker build machine. | 1 | Finished As Planned | Stuart Higgins
normal | Task | Test Python ducttape API client | 2 | Finished As Planned | Tucker Siemens
normal | Task | Buildweb GCP Beta poll_gcp_resources | 3 | Finished As Planned | Forest Clay
normal | Task | Deploy Regression wheel QAVM in GCP | 2 | Finished As Planned | Stuart Higgins
normal | Task | Create PIP package for Image-Maker | 3 | Finished As Planned | Stuart Higgins
normal | Task | Validate new ducttape API v2.0 deployment | 1 | Finished As Planned | Tucker Siemens
normal | Task | Deploy new ducttape API v2.0 to staging | 1 | Finished As Planned | Tucker Siemens
normal | Task | Puppetize any potential ducttape API v2.0 changes | 1 | Finished As Planned | Tucker Siemens
normal | Task | Imagemaker Build Job DDD | 4 | Doing Now | Evan Cramer
normal | Task | CLI work for the client | 3 | Doing Now | Tucker Siemens
normal | Task | Add Jenkins GCP Build Call to Ducttape | 1 | Current Sprint Backlog | Reilly Steele
normal | Task | Improve the imagemaker tool | 0 | Backlog | Evan Cramer, Daniel Gonzalez, Tucker Siemens
normal | Task | GCP - Run the latest BR_PIPE_DEV and annotate results | 3 | Discarded or Obsolete | Mark Taylor
normal | Task | GCP - Annotate a new regression run on Pipeline | 1 | Discarded or Obsolete | Mark Taylor
normal | Task | Write supporting CLI test code (fixtures, mocks, etc.) | 1 | Current Sprint Backlog | Tucker Siemens
normal | Task | Investigate testing of Click applications | 1 | Current Sprint Backlog | Tucker Siemens
normal | Task | Imagemaker Jenkins job PoC | 1 | Finished As Planned | Alba Magallanes
normal | Task | GCP - Annotate a new BVT run on Pipeline | 1 | Finished As Planned | Mark Taylor
normal | Task | Buildweb GCP Beta Database Schema | 2 | Finished As Planned | Forest Clay
normal | Task | Buildweb GCP Beta request_gcp_resource | 3 | Finished As Planned | Forest Clay
normal | Task | Disallow unsupported configuration options for GCP clusters in the ducttape api | 1 | Finished As Planned | Reilly Steele
normal | Task | Add GCPClusterManager to Ducttape | 3 | Finished As Planned | Reilly Steele
normal | Task | Client Config DDD | 3 | Finished As Planned | Reilly Steele
normal | Task | Update Python ducttape API client to work with new API v2.0 routes | 2 | Finished As Planned | Tucker Siemens
normal | Task | Re-enable snapshot support in Ducttape | 3 | Finished As Planned | Reilly Steele
normal | Task | GCP Project DDD | 5 | Finished As Planned | Reilly Steele, Greg Bristol
normal | Task | Taskmaster: Endpoint to generate random rig passwords for buildweb tasks | 1 | Backlog | Evan Cramer
normal | Task | Add functionality to create a vsphere client directly from a template | 3 | Backlog | Reilly Steele
normal | Task | Test snapshot support in Ducttape | 3 | Doing Now | Reilly Steele
normal | Task | Add GCPClusterManager Tests | 3 | Discarded or Obsolete | Reilly Steele
normal | Task | Aggregate GCP Security Concerns for Daniel Gonzalez | 3 | Backlog | Tucker Siemens
normal | Task | Modify buildweb dole commands for GCP docker test launching | 1 | Under Review | Stuart Higgins
normal | Task | Remove all direct BuildDB access from Taskmaster | 1 | Backlog | Greg Bristol
normal | Task | DuctTape API integration for dynamic clients | 4 | Backlog | Greg Bristol, Forest Clay
normal | Task | DuctTape API integration for virtual clusters (killing champion) | 4 | Backlog | Greg Bristol, Forest Clay
normal | Task | Talk to core about any new bug found in their court | 1 | Finished As Planned | Daniel Gonzalez
normal | Task | Merge ducttape API v1 and API v2 | 3 | Finished As Planned | Tucker Siemens
normal | Task | Create machine.id library for use in GCP vCluster creation | 3 | Finished As Planned | Tucker Siemens
normal | Task | Test for the CLI client work | 3 | Current Sprint Backlog | Tucker Siemens
normal | Task | Investigate changes to FreeBSD puppet config | 3 | Finished As Planned | Stuart Higgins
normal | Task | Deploy FreeBSD dev machine for image maker/puppet work | 1 | Finished As Planned | Stuart Higgins
normal | Task | Investigate FreeBSD11/12 options | 1 | Finished As Planned | Stuart Higgins
normal | Task | Client Config PSA | 1 | Finished As Planned | Reilly Steele
normal | Task | GCP - Annotate a new Dev Regression run on Pipeline | 3 | Finished As Planned | Mark Taylor
normal | Task | Sprint 20180129 Sustaining Tasks - gbristol | 2 | Finished As Planned | Greg Bristol
normal | Task | Investigate ACS node join non-determinism and file bug | 1 | Finished As Planned | Greg Bristol
normal | Task | Investigate alternatives to accelerate BVT and dev_reg delivery to core engineering | 2 | Finished As Planned | Reilly Steele, Greg Bristol, Forest Clay
normal | Task | Add GCP logserver to logindex | 1 | Finished As Planned | Greg Bristol
normal | Task | Imagemaker build job PoC | 3 | Finished As Planned | Evan Cramer, Alba Magallanes
normal | Task | GCP - Run the latest BR_PIPE_DEV and annotate results (2nd week) | 3 | Started but not Finished | Mark Taylor
normal | Task | Complete python pip packaging of Imagemaker | 2 | Started but not Finished | Evan Cramer
normal | Task | Write Salt-states readme | 1 | Backlog
normal | Task | Research & apply GCP External IP security policy | 1 | Backlog
normal | Task | Write client salt state | 3 | Backlog | Tucker Siemens
normal | Task | GCP test task for reilly | 3 | Discarded or Obsolete | Reilly Steele

## Metadata
Metadata
normal | Task | Test multi cluster configuration` | 3 | Finished As Planned | Greg Bristol
normal | Task | Investigate strategies for iterative metadata deployment | 3 | Doing Now | Greg Bristol
normal | Task | Metadata iterative deployment PSA | 2 | Current Sprint Backlog | Greg Bristol
normal | Epic | Metadata - Virtual Provisioning | 0 | Backlog
normal | Epic | Metadata - OneFS changes | 0 | Backlog
normal | Task | Stage new Pooling code | 1 | Backlog | Greg Bristol
normal | Epic | Metadata - Testing and Integration | 0 | Backlog
normal | Epic | Metadata- Physical Provisioning | 0 | Backlog
normal | Epic | Metadata - Buildweb changes | 0 | Backlog
normal | Task | Fix bugs exposed in system integration testing in Buildweb | 10 | Backlog | Forest Clay
normal | Task | Update resource ready callback unit tests for new format in Buildweb | 2 | Backlog | Forest Clay
normal | Task | Metadata Test Plan: BR_MR_8_0_1_X | 2 | Backlog | Forest Clay
normal | Task | Metadata Test Plan: BR_MR_8_1_0_X | 2 | Backlog | Forest Clay
normal | Task | Metadata Test Plan: Niijima | 2 | Backlog | Forest Clay
normal | Task | Metadata Test Plan: Pool configs | 5 | Backlog | Forest Clay
normal | Task | Metadata Test Plan: Webui Changes | 2 | Backlog | Forest Clay
normal | Task | Metadata Test Plan: Task Configs | 3 | Backlog | Forest Clay
normal | Task | Metadata Test Plan: BR_MR_8_0_0_X | 2 | Backlog | Forest Clay
normal | Task | Metadata Test Plan: Setup overhead | 3 | Backlog | Forest Clay
normal | Task | Add UI to generate XML for users | 4 | Backlog | Alba Magallanes
normal | Task | Validation: Taskmaster resource_ready_callback | 2 | Backlog | Evan Cramer
normal | Task | Test Quarantine rigs directly in buildweb | 2 | Backlog | Forest Clay
normal | Task | Generate dynamic resource checkin URLs in Buildweb | 2 | Backlog | Forest Clay

## Code Coverage for Pipeline Buil
Code Coverage for Pipeline Builds
normal | Task | Diff coverage demo | 0 | Current Sprint Backlog | Piyush Diwan
normal | Task | Code Coverage: HTML reporting for diff code | 0 | Current Sprint Backlog | Piyush Diwan
normal | Task | Wiki update for :https://wiki.west.isilon.com/index.php/Code_Coverage_For_New_Code | 1 | Finished As Planned | Piyush Diwan
normal | Task | Bug 220697 | 1 | Current Sprint Backlog | Paresh Naik
normal | Task | Code coverage : Merge @ Build & Branch | 3 | Doing Now | Ton Oguara
normal | Task | Code coverage : Provide CC report roll-up for TP1 | 3 | Current Sprint Backlog | Ton Oguara
normal | Task | Code coverage : Diff & Merge | 3 | Current Sprint Backlog | Ton Oguara
normal | Task | CC report for new / modified files-Testing | 2 | Finished As Planned | Piyush Diwan
normal | Task | CC report for new / modified files-Coding | 3 | Finished As Planned | Piyush Diwan
normal | Task | CC report for new / modified files-Research | 2 | Finished As Planned | Piyush Diwan
normal | Task | Analyse results and file bugs for identified failures | 2 | Finished As Planned | Paresh Naik
normal | Task | Re-run tests for resolved bugs | 1 | Finished As Planned | Paresh Naik
normal | Task | Identify testlists to be executed (lists that are not yet executed for CC on RW) and update wiki table to track the execution | 1 | Finished As Planned | Paresh Naik
normal | Task | Yet another bugs sprint - Bugs for sprint 2/26 - 3/9 | 10 | Finished As Planned | Ton Oguara
normal | Task | Fix bug 219750 | 2 | Finished As Planned | dharmender jain
normal | Task | Fix bug 218189 | 5 | Finished As Planned | dharmender jain
normal | Task | Integrate more comprehensive json validation with Travis CI | 3 | Finished As Planned | Ton Oguara
normal | Task | Queue all tests that are never run before on RW for CC | 2 | Finished As Planned | Paresh Naik
normal | Task | Find testlists for which mapping JSON need to be updated and update wiki | 2 | Finished As Planned | Paresh Naik
normal | Task | Fix bug 217704 | 2 | Finished As Planned | dharmender jain
normal | Task | Fix bug 217799 | 3 | Finished As Planned | dharmender jain
normal | Task | Finding Orphans CC targets (Targets not defined or captured in any json file) | 0 | Backlog | Ton Oguara
normal | Task | Convert code coverage trace file to json for easy reporting and portability | 0 | Backlog | Ton Oguara
normal | Task | Breakdown CC report by legacy and new code | 0 | Backlog | Ton Oguara
normal | Task | CC Roll out- Champions & Brown Bag Prep and Presentation | 0 | Finished As Planned | Ton Oguara
normal | Task | Work on Assigned Bugs 216648 - ds_data_management.list | 0 | Finished As Planned | Paresh Naik
normal | Task | Work on Assigned Bugs 217313 - papi_functional_tests.list | 0 | Finished As Planned | Paresh Naik
normal | Task | RCA Bug 217799 | 0 | Finished As Planned | dharmender jain
normal | Task | Improve Code Coverage report Merging | 0 | Backlog | Ton Oguara
normal | Task | Ton's bug for sprint 1/29-2/9 | 7 | Finished As Planned | Ton Oguara
normal | Task | Work on Assigned Bugs 215548 | 0 | Finished As Planned | Paresh Naik
normal | Task | Work on Assigned Bugs 207999 | 0 | Finished As Planned | Paresh Naik
normal | Task | Work on Assigned Bugs 207576 | 0 | Finished As Planned | Paresh Naik
normal | Task | Failure analysis for B_PIPE_DEV_789 build RW runs - Part 2 | 0 | Finished As Planned | Paresh Naik
normal | Task | Work on Assigned Bugs 210501 | 0 | Finished As Planned | Paresh Naik
normal | Task | Write a proposal for : Dev Regression, Smoke, Apps, bvt.list | 0 | Backlog | Ton Oguara
normal | Task | isi_nfs(D to register a bug - T to discuss w/ David K on disabling test for Code Coverage ), | 0 | Backlog | Ton Oguara
normal | Task | Protocols: Work with Rudolfo to complete the encryption SMB test run | 0 | Discarded or Obsolete | Ton Oguara
normal | Task | Failure analysis for B_PIPE_DEV_789 build RW runs - Part 1 | 0 | Finished As Planned | Paresh Naik
normal | Task | Code coverage Bug Scrubbing | 0 | Finished As Planned | Paresh Naik
normal | Task | Figure out how to replace Ton's private Git Hash key | 0 | Backlog | Ton Oguara
normal | Task | Update wiki before roll out | 0 | Finished As Planned | Piyush Diwan
normal | Task | Try instrumenting the code for PerfBVT. If not successful, open a bug | 0 | Finished As Planned | Paresh Naik
normal | Task | Discuss with PL Leads: failure analysis process, targets for fsds_bvt, Statview issues,all MVT for branch | 0 | Finished As Planned | Ton Oguara, Sonal Agarwal
normal | Task | SST:Add SST coverage Update to CC wiki | 0 | Finished As Planned | Paresh Naik
normal | Task | Paltforms: Try h/w mapping and check if instrumentation works | 0 | Finished As Planned | Paresh Naik
normal | Task | FSDS: Kick off fsds_bvt on entire fsds targets | 0 | Finished As Planned | dharmender jain
normal | Task | Protocols:Add Protocols coverage to Protocols CC wiki | 0 | Finished As Planned | Paresh Naik
normal | Task | FSDS: Update the PL CC wiki as FSDS tests complete run | 0 | Finished As Planned | Paresh Naik, dharmender jain

## scripts management going forwar
scripts management going forward

## DataIQ Mainteanance
DataIQ Mainteanance
normal | Task | Additional work for adhoc request (bug# 218752) | 3 | Doing Now | Ganesh Prabhu
normal | Task | Adhoc bug bash | 1 | Current Sprint Backlog | Ganesh Prabhu, Ethan Madden, Brooks Kindle, Edward Hodapp
normal | Task | `Perform subdivided DB queries to extract subsets of the SMART drive schemas. | 3 | Finished As Planned | Edward Hodapp
normal | Task | Adhoc bug bash | 1 | Finished As Planned | Ganesh Prabhu, Ethan Madden, Brooks Kindle, Edward Hodapp
high | Task | Generate adhoc report for interface types in network pools. | 1 | Finished As Planned | Edward Hodapp
normal | Task | Create code to populate DataIQ approved drive table when DSP changes detected. | 3 | Next Sprint Planning | Edward Hodapp
normal | Task | Create DataIQ table for approved drive make and models. | 3 | Next Sprint Planning | Edward Hodapp
normal | Task | Adhoc bug 217490 | 3 | Current Sprint Backlog | Ethan Madden
normal | Task | Create code to poll for changes in the Drive Support Package (DSP) | 3 | Next Sprint Planning | Edward Hodapp
normal | Task | Adhoc bug bash | 1 | Finished As Planned | Ganesh Prabhu, Ethan Madden, Brooks Kindle, Edward Hodapp

## CloudIQ
CloudIQ
normal | Task | Scope the project to send IPH data directly to CloudIQ | 3 | Finished As Planned | Ganesh Prabhu
normal | Task | CloudIQ ESRS Service Configuration | 3 | Current Sprint Backlog | Daniel Gonzalez
normal | Task | Investigating how do we push IPH data to CloudIQ (part2) | 3 | Finished As Planned | Shaun Edwards
normal | Task | Investigating how do we push IPH data to CloudIQ | 3 | Finished As Planned | Shaun Edwards
normal | Task | Make sure that the telemetry agent in 8.1.0.3 is pushing the right data | 2 | Doing Now | Shaun Edwards
normal | Task | Freight Trains 8.1.0.3 & CloudIQ Integration Testing | 3 | Backlog | Shaun Edwards
normal | Epic | Create Isilon System Adapter Plugin | 0 | Backlog | Dan Forrest
normal | Task | Take on the product owner tasks for CloudIQ | 2 | Current Sprint Backlog | Daniel Gonzalez
normal | Task | Drive the process to create the tunnel between ESRS/CloudIQ | 3 | Current Sprint Backlog | Daniel Gonzalez
normal | Epic | Create Isilon Data Processor Microservice | 0 | Current Sprint Backlog | Shaun Edwards
normal | Task | cloudiq test | 0 | Discarded or Obsolete | Dan Forrest, Shaun Edwards

## ServiceNow Taskmaster Integra
ServiceNow / Taskmaster Integration
normal | Task | Write Isilon::SerrviceNow module | 3 | Doing Now | Stuart Higgins
normal | Task | Work with Service Now on linking DB fields and access for the dev/staging environments. | 3 | Under Review | Stuart Higgins
normal | Task | ESM Integration: Requirements collection and investigation | 3 | Finished As Planned | Stuart Higgins
normal | Task | Make changes to Server table and User table on dev taskmaster | 1 | Under Review | Stuart Higgins
normal | Task | Taskmaster::DB::Server changes | 3 | Doing Now | Stuart Higgins
normal | Task | Create a script to update employeeID for users in Taskmaster | 1 | Current Sprint Backlog | Stuart Higgins
normal | Task | Add changes to Taskmaster user table | 2 | Current Sprint Backlog | Stuart Higgins
normal | Task | Begin writing DDD for Tasmaster/ServiceNow integration | 3 | Under Review | Stuart Higgins
normal | Task | Create Taskmaster/MachineDB servers for ServiceNow testing | 1 | Finished As Planned | Stuart Higgins

## IPv6 Testing in Durham
IPv6 Testing in Durham
normal | Task | IOS code upgrades | 2 | Current Sprint Backlog | Phong Truong
normal | Task | IPv6: Assess current ASR hardware and cabling | 2 | Finished As Planned | Phong Truong
normal | Task | IPv6: Procure any missing NICs/modules | 4 | Finished As Planned | Phong Truong
normal | Task | Finalize topology and design | 3 | Under Review | Phong Truong
normal | Task | Build NAT64 configs | 4 | Next Sprint Planning | Phong Truong
normal | Task | Build GRE tunnel configs | 4 | Next Sprint Planning | Phong Truong

## Opengrok OpengrokVM Scripting
[Opengrok] OpengrokVM Scripting and Deploy
normal | Task | [Opengrok]Enable Nginx SSL and SSL redirect | 3 | Finished As Planned | Xuan Du, Jimmy Sun, guoyun wang, Tom Liu
normal | Task | [Opengrok]Fix Opengrok/Git update issue | 3 | Finished As Planned | Xuan Du, Jimmy Sun, guoyun wang, Tom Liu
normal | Task | [Opengrok] production deploy of 1st opengrok server via puppet | 0 | Finished As Planned | Xuan Du, Jimmy Sun, Tom Liu
normal | Task | [Opengrok] staging tests | 0 | Finished As Planned | Xuan Du, Jimmy Sun, Tom Liu
normal | Task | [Opengrok] opengrok install and config scripts | 0 | Finished As Planned | Xuan Du, Jimmy Sun, Tom Liu
normal | Task | [Opengrok] puppet coding for deploy opengrok server | 0 | Finished As Planned | Xuan Du, Jimmy Sun, Tom Liu
normal | Task | [Opengrok] POC for transform docker version opengrok into vm version | 0 | Finished As Planned | Xuan Du, Jimmy Sun, Tom Liu
normal | Task | [Opengrok] git checkout scripts | 0 | Finished As Planned | Xuan Du, Jimmy Sun, Tom Liu
normal | Task | [Opengrok] eyaml integration testing | 0 | Finished As Planned | Xuan Du, Jimmy Sun, Tom Liu
normal | Task | [Opengrok] base enviornment setup scripts | 0 | Finished As Planned | Xuan Du, Jimmy Sun, Tom Liu
normal | Task | [Opengrok] nginx install and config scripts | 0 | Finished As Planned | Xuan Du, Jimmy Sun, Tom Liu
normal | Task | [Opengrok] LDAPs integration testing | 0 | Finished As Planned | Xuan Du, Jimmy Sun, Tom Liu
normal | Task | [Opengrok] opengrok indexing and updating scripts | 0 | Finished As Planned | Xuan Du, Jimmy Sun, Tom Liu
normal | Task | [Opengrok] tomcat install and config scripts | 0 | Finished As Planned | Xuan Du, Jimmy Sun, Tom Liu
normal | Task | [Opengrok] code review | 0 | Finished As Planned | Xuan Du, Jimmy Sun, Tom Liu

## Regression Wheel Firmware upgra
Regression Wheel Firmware upgrade
normal | Task | Ingest - Seattle Nodes - Wingfeet | 2 | Finished As Planned | Jimmy Sun, guoyun wang, Tom Liu
normal | Task | Ingest - Durham Nodes - Blueflames | 3 | Finished As Planned | Jimmy Sun, Tom Liu

## vROPs Seattle and Durham setu
[vROPs] Seattle and Durham setup
normal | Task | [vROPs] durham-seattle firewall openning request | 5 | Doing Now | Xuan Du, Jimmy Sun, Tom Liu
normal | Task | [vROPs] config access and role for DESKTOP users | 1 | Backlog | Xuan Du, Jimmy Sun, Tom Liu
normal | Task | [vROPs] import initail general dashboard | 1 | Backlog | Xuan Du, Jimmy Sun, Tom Liu
normal | Task | [vROPs] durham demo site destroy | 1 | Backlog | Xuan Du, Jimmy Sun, Tom Liu
normal | Task | [vROPs] durham site remote collecter deploy | 3 | Backlog | Xuan Du, Jimmy Sun, Tom Liu
normal | Task | [vROPs] durham site remote collecter config | 3 | Backlog | Xuan Du, Jimmy Sun, Tom Liu
normal | Task | [vROPs] durham site license application | 5 | Backlog | Xuan Du, Jimmy Sun, Tom Liu
normal | Task | [vROPs] durham demo site deploy | 0 | Finished As Planned | Xuan Du, Jimmy Sun, Tom Liu
normal | Task | [vROPs] main site (seattle) deploy | 0 | Finished As Planned | Xuan Du, Jimmy Sun, Tom Liu
normal | Task | [vROPs] create general and sample dashboard | 0 | Finished As Planned | Xuan Du, Jimmy Sun, Tom Liu

## Pull Request Automation and Man
Pull Request Automation and Management Tools
normal | Task | Write up a PSA for the MR(PR) release automation project | 1 | Next Sprint Planning | Brooks Kindle

## Automated Test Scheduler Rework
Automated Test Scheduler Rework
normal | Task | Re-test and deploy | 2 | Current Sprint Backlog | Alba Magallanes
normal | Task | Puppetize the auto scheduler changes | 2 | Doing Now | Alba Magallanes
normal | Task | Remove dependency on metadata | 2 | Current Sprint Backlog | Alba Magallanes

## PXE Taskmaster Integration
PXE Taskmaster Integration
normal | Task | Bug 213046: Lazarus Serial Console Logging | 4 | Backlog | Evan Cramer

## Formalize Isilon-CEE infrastruc
Formalize Isilon-CEE infrastructure and decide on config management schema, if any

## Host Packet Capture Analyzer to
Host Packet Capture Analyzer tool on Eng Inf
normal | Task | Host elasticsearch instance on eng-automation server (elasticsearch.elk.apps.isilon.com:9200) | 0 | Backlog | Ganesh Prabhu
normal | Task | Run Pcap task and Web app with lab credentials | 0 | Backlog | Ganesh Prabhu

## Replace existing version of Pup
Replace existing version of Puppet with SALT M1
normal | Task | Saltstack PSA | 3 | Doing Now | Ethan Madden

## DataIQ 1.5
DataIQ 1.5
normal | Task | Promote DataIQ 1.5 to prod | 1 | Finished As Planned | Ethan Madden
normal | Task | Test pre-release of DataIQ 1.5 | 3 | Finished As Planned | Ethan Madden, Guillaume THOMAS
normal | Task | Promote DataIQ 1.5 to stage | 1 | Finished As Planned | Ethan Madden, Guillaume THOMAS
normal | Task | Promote DataIQ 1.5 to prod | 1 | Finished As Planned | Ethan Madden, Guillaume THOMAS

## Code Coverage Improvements fo
Code Coverage : Improvements for isi_coverage.sh
normal | Task | Fix Bug isi_coverage.sh - 217456 | 1 | Finished As Planned | dharmender jain
normal | Task | Fix Bug isi_coverage.sh - 217519 | 2 | Finished As Planned | dharmender jain
normal | Task | Preapare Test Plan for isi_coverage.sh | 2 | Finished As Planned | Paresh Naik
normal | Task | Fix isi_coverage.sh bug - 217457 | 3 | Finished As Planned | dharmender jain
normal | Task | Identify issues with isi_coverage.sh and open bugs for them | 2 | Finished As Planned | dharmender jain

## MR Branch & Release Automation
MR Branch & Release Automation
normal | Task | Create initial MR Branch Process Overview | 1 | Finished As Planned | Rick Ludvigsen
normal | Task | Create initial MR Branch Process Overview - 2 | 1 | Current Sprint Backlog | Rick Ludvigsen

## Evaluate vRealize Automation fo
Evaluate vRealize Automation for internal cloud use
normal | Task | Deploy vRealize Instance to Dev Environment | 3 | Current Sprint Backlog | Daniel Mills

## Artifactory Production Upgrade
Artifactory Production Upgrade & Resource Tuning
normal | Task | Artifactory Tomcat JVM heap size change-research | 3 | Finished As Planned | Wade Naveja
normal | Task | Artifactory Production VM CPU Tuning | 1 | Finished As Planned | Wade Naveja
normal | Task | Artifactory Service Version Upgrade | 0 | Next Sprint Planning | Wade Naveja

## Artifactory HTTPS Support
Artifactory HTTPS Support
normal | Task | Create & Test Artifactory nginx reverse proxy config with support for SSL | 0 | Backlog | Wade Naveja

## Artifactory Tier 1 SLA Complian
Artifactory Tier 1 SLA Compliance-Reqs & analysis

## Artifactory Dev & Stage Environ
Artifactory Dev & Stage Environment Refresh
normal | Task | Deploy New Artifactory Dev Server | 2 | Doing Now | Wade Naveja
normal | Task | Deploy New Artifactory Staging Server | 2 | Current Sprint Backlog | Wade Naveja

## Artifactory rpm repo archiving
Artifactory rpm repo archiving plug-in install & configuration
normal | Task | Archiving plug-in configuration | 1 | Next Sprint Planning | Wade Naveja
normal | Task | Archiving plug-in deploy | 1 | Finished As Planned | Wade Naveja

## Relocate SSDs from Build hosts
Relocate SSDs from Build hosts to T1 Cluster
normal | Task | Test live removal of SSDs from Lenovo and Dell Hosts | 1 | Finished As Planned | Daniel Mills, Rick Ludvigsen
normal | Task | Remove SSDs from all Dell and Lenovo Hosts | 1 | Finished As Planned | Daniel Mills
normal | Task | Add SSDs to new VSAN disk groups | 1 | Finished As Planned | Daniel Mills

## Deployment of Build Artifact Ch
Deployment of Build Artifact Changes for Bug 196150
normal | Task | Deployment of Build Artifact Changes for Bug 196150 | 1 | Finished As Planned | Rick Ludvigsen

## Deployment of Build Executor Ve
Deployment of Build Executor Version 258
normal | Task | Deployment of Build Executor 258 | 2 | Finished As Planned | Rick Ludvigsen

## RW H W Swap & CAPEX (trading wi
RW H/W Swap & CAPEX (trading with compression team)
normal | Task | Figure Out DVT Hotfoot CTO issues | 1 | Finished As Planned
normal | Task | Upgrade/Replace LOx cards on HF005, HF006, HF007 | 1 | Finished As Planned

## Incremental Build Support - DUP
Incremental Build Support - DUPLICATE

## Code Coverage Resource Utilizat
Code Coverage Resource Utilization on RW

## Corruption Tool
Corruption Tool
normal | Task | Create PSA and t-shirt size the corruption tool project | 1 | Under Review | Brooks Kindle

## Comprehensive DEBUG patch handl
Comprehensive DEBUG patch handling

## Jenkins Upgrade
Jenkins Upgrade
normal | Task | Jenkins 2.X Planning and Requirements - 2 | 3 | Finished As Planned | Rick Ludvigsen
normal | Task | Jenkins 2.X Planning and Requirements - 3 | 3 | Doing Now | Rick Ludvigsen
normal | Task | Jenkins 2.X Planning and Requirements - 1 | 1 | Finished As Planned | Rick Ludvigsen
normal | Task | Perform performance analysis of new Jenkins on VM. | 3 | Current Sprint Backlog | Rick Ludvigsen, Guillaume THOMAS

## GCP (TEaaS) - M4
GCP (TEaaS) - M4
normal | Task | DT schema changes for /environments/ | 3 | Current Sprint Backlog | Forest Clay
normal | Task | DT implement /environments/ API endpoint | 3 | Current Sprint Backlog | Forest Clay
normal | Task | Write unit tests for /environments/ endpoint | 3 | Backlog | Forest Clay
normal | Task | Duct Tape /environment/ DDD | 3 | Finished As Planned | Forest Clay
normal | Task | Investigate DT source code and database schema | 3 | Finished As Planned | Forest Clay
normal | Task | Add multi-cluster configuration support to PoolService | 2 | Finished As Planned | Greg Bristol
normal | Task | Gather infrastructure requirements from Engineering | 3 | Current Sprint Backlog | Daniel Gonzalez
normal | Task | DT documentation for /environments/ endpoint | 2 | Backlog | Forest Clay
normal | Task | DT API alter /clusters/ and /clients/ endpoints to use /environments/ logic | 3 | Backlog | Forest Clay
normal | Task | DT integration testing for /environments/ work | 3 | Backlog | Forest Clay

## Train Jimmy, Tom, Bill, & Mark
Train Jimmy, Tom, Bill, & Mark
normal | Task | Rewrite personal notes as System Quarantined Node Runbook | 2 | Finished As Planned
normal | Task | Triage & Delegate | 1 | Finished As Planned

## Leankit integration & reporting
Leankit integration & reporting

## Code Coverage for normal Python
Code Coverage for normal Python code in OneFS
normal | Task | Tests development for Python Code Coverage | 3 | Backlog | Piyush Diwan
normal | Task | Python Code Coverage POC - Branch coverage | 3 | Finished As Planned | Piyush Diwan
normal | Task | Python Code Coverage POC - line coverage | 3 | Finished As Planned | Piyush Diwan
normal | Task | Python Code Coverage POC - Function coverage | 3 | Finished As Planned | Piyush Diwan
normal | Task | PSA for Python code-coverage | 3 | Finished As Planned | Piyush Diwan
normal | Task | Python Code Coverage POC | 2 | Finished As Planned | Piyush Diwan
normal | Task | Python CC PSA research | 3 | Finished As Planned | Piyush Diwan

## OneFS Simulator Test automation
OneFS Simulator Test automation

## Project status reporting (web s
Project status reporting (web server)
normal | Task | Leankit API V2 - python wrapper | 2 | Finished As Planned | Guillaume THOMAS
normal | Task | Leankit - Data processing | 2 | Doing Now | Guillaume THOMAS

## VCenter Harmonization, Moderniz
VCenter Harmonization, Modernization and Expansion
normal | Task | Create reports for vCenter utilization by team | 1 | Finished As Planned | Daniel Mills
normal | Task | Create reports for Idle VMs | 1 | Finished As Planned | Daniel Mills

## Convert existing CC scripts to
Convert existing CC scripts to Python

## Review Board Upgrade
Review Board Upgrade

## Code Coverage weekly report
Code Coverage weekly report

## Code Coverage for NJ
Code Coverage for NJ

## Bug reports for MRs
Bug reports for MRs

## Code Coverage Incorporate Web
Code Coverage : Incorporate WebUI CC

## Code Coverage Root Partition
Code Coverage : Root Partition issue on vOneFS

## Code Coverage NDU
Code Coverage: NDU

## Automated Patches M3
Automated Patches M3

## Quarantine Nag Mail for Leads
Quarantine Nag Mail for Leads

## Wiki Salt automation and versio
Wiki Salt automation and version upgrade

## Composable Release Support
Composable Release Support
normal | Request | RW support for running lists on different branches | 0 | New Requests | Daniel Gonzalez
normal | Request | RW Support for Automated Patch Installation | 0 | New Requests | Guillaume THOMAS

## Code Coverage Dev & TestMgr Wo
Code Coverage :Dev & TestMgr Workflow
normal | Task | Add support for FSP/likewise selective targets instrumentation | 0 | Backlog
normal | Task | Update wiki dev workflows w/ other approaches to CC for core developers | 0 | Finished As Planned | Piyush Diwan
normal | Task | isi_coverage.sh - Raise the PR | 0 | Finished As Planned | dharmender jain

## Formal mapping of ignored files
Formal mapping of ignored files for correlation

## Functional script verification
Functional script verification & testing integration

## Replace and decommission patch
Replace and decommission patch upload

## Reviewboard ship-it verificatio
Reviewboard ship-it verification & auto-updates

## Removal of XML preview usage fr
Removal of XML preview/usage from spog and inputs

## Ability to pre-install matching
Ability to pre-install matching customer patches on cluster pre-mechanics testing

## RW – Shanghai Onboarding
RW – Shanghai Onboarding

## CC for Python bindings
CC for Python bindings

## Code Coverage in Regression Whe
Code Coverage in Regression Wheel
normal | Task | Incorporate CC scripts to buildweb | 0 | Finished As Planned | Ton Oguara
normal | Task | Kick off Virtualized MVT tests matching PL leads list from buildweb off Ton's private branch | 0 | Finished As Planned | Ton Oguara, Paresh Naik
normal | Task | Send out CR for CC code with Buildweb integration | 0 | Finished As Planned | Ton Oguara
normal | Task | Kick off FSDS MVT tests matching PL leads list from buildweb off Ton's private branch | 0 | Finished As Planned | Ton Oguara, Paresh Naik

## Code Coverage for Niijima Build
Code Coverage for Niijima Builds

## PXE Firmware upgrade via Taskma
PXE Firmware upgrade via Taskmaster

## PXE firmware upgrade support
PXE firmware upgrade support

## Duct Tape client provisioning
Duct Tape client provisioning

## Mandatory Test List Timeouts
Mandatory Test List Timeouts

## Elastic (ELK) Log Stack
Elastic (ELK) Log Stack

## Legacy Firmware Updates
Legacy Firmware Updates