## Projects
Project | createdOn | Nb Days | Column | Assigned to | Initial ECD | Current ECD | Blocked
Research and Deploy Superna Eyeglass for cluster config backup | 03/13/2018 | 2 | Scoping | Richard Blalock
Data Retention | 03/12/2018 | 2 | Scoping | Richard Blalock
InsightIQ Upgrade | 03/12/2018 | 2 | Scoping | Richard Blalock
OneFS Upgrade cadence | 03/12/2018 | 2 | Scoping | Richard Blalock
Research and Facilitate OneFS GS training | 03/12/2018 | 2 | Scoping | Richard Blalock
Dell Lab Standard and Safety Training | 03/12/2018 | 3 | Finished As Planned | Richard Blalock
Reduce time to market | 03/10/2018 | 5 | New Requests | Greg Bristol, Daniel Gonzalez
Centralized Database | 03/09/2018 | 5 | Scoping | Reilly Steele, Daniel Gonzalez
Versioned patch data project | 03/02/2018 | 12 | In Design | Chris Tabor, Guillaume THOMAS
Move from patch db model to a git based model | 03/02/2018 | 12 | New Requests | Chris Tabor, Guillaume THOMAS
ImageMaker Integration | 02/28/2018 | 14 | In Progress | Robert Haddon, Guillaume THOMAS
Cluster monitoring automation | 02/28/2018 | 15 | Scoping | Vince Thyng, Guillaume THOMAS
Upgrade/rollback automation for patches | 02/26/2018 | 16 | Scoping | Chris Tabor, Guillaume THOMAS
Upgrade/rollback automation PSA for patches | 02/26/2018 | 16 | Scoping | Chris Tabor, Guillaume THOMAS
Code Coverage Resource Utilization on RW | 02/26/2018 | 16 | New Requests | Ananthan Pillai
scripts management going forward | 02/26/2018 | 16 | New Requests | Chris Tabor, Guillaume THOMAS
Metadata | 02/23/2018 | 20 | In Progress | Greg Bristol, Daniel Gonzalez
DataIQ Mainteanance | 02/22/2018 | 21 | In Progress | Guillaume THOMAS
DataIQ | 02/22/2018 | 21 | In Progress | Guillaume THOMAS
save_logs deployment | 02/19/2018 | 23 | Finished As Planned | Daniel Gonzalez, Alba Magallanes | 03/02/2018 | 03/02/2018
Seattle Distribution Switch Overhaul | 02/16/2018 | 26 | In Progress | Ananthan Pillai, Phong Truong | 03/30/2018 | 03/30/2018
SyncIQ Policy Review and Remediation | 02/16/2018 | 26 | In Progress | Richard Blalock, Guillaume THOMAS
Formalize Isilon-CEE infrastructure and decide on config management schema, if any | 02/16/2018 | 27 | Scoping | Jesse Rhodes, Guillaume THOMAS
Research and deploy production ESRS gateway | 02/14/2018 | 28 | In Progress | Richard Blalock, Guillaume THOMAS
ESRS server | 02/14/2018 | 28 | Scoping | Richard Blalock, Guillaume THOMAS
Relocate SSDs from Build hosts to T1 Cluster | 02/14/2018 | 28 | Finished As Planned | Daniel Mills, Guillaume THOMAS
DR & Backup for Eng Inf | 02/14/2018 | 29 | Scoping | Richard Blalock, Guillaume THOMAS
mechanics automation "v2" | 02/08/2018 | 34 | New Requests | Chris Tabor, Guillaume THOMAS
v4.1 live ongoing | 02/08/2018 | 34 | Finished As Planned | Chris Tabor, Guillaume THOMAS | 03/15/2018 | 03/15/2018
Train Jimmy, Tom, Bill, & Mark | 02/08/2018 | 34 | Finished As Planned
Artifactory HTTPS Support | 02/08/2018 | 34 | Approved | Wade Naveja, Guillaume THOMAS
Artifactory Tier 1 SLA Compliance-Reqs & analysis | 02/08/2018 | 34 | Scoping | Wade Naveja, Guillaume THOMAS
Artifactory Dev & Stage Environment Refresh | 02/08/2018 | 34 | In Progress | Wade Naveja, Guillaume THOMAS | 03/23/2018 | 03/23/2018
Artifactory rpm repo archiving plug-in install & configuration | 02/08/2018 | 34 | In Progress | Wade Naveja, Guillaume THOMAS |  |  | Blocked
Github Enterprise Appliance Upgrade | 02/08/2018 | 34 | Finished As Planned | Wade Naveja, Guillaume THOMAS | 03/09/2018 | 03/09/2018
Regression Wheel Firmware upgrade | 02/08/2018 | 35 | Finished As Planned | Jimmy Sun, Tom Liu
[Opengrok] OpengrokVM Scripting and Deploy | 02/08/2018 | 35 | Finished As Planned | Xuan Du, Jimmy Sun, Tom Liu | 03/05/2018 | 03/05/2018
[vROPs] Seattle and Durham setup | 02/07/2018 | 36 | In Progress | Xuan Du, Jimmy Sun, Tom Liu | 03/30/2018 | 03/30/2018 | Blocked
[vROPs] VCenter Dashboard | 02/07/2018 | 36 | In Progress | Xuan Du, Jimmy Sun, Tom Liu
Parser toolkit project | 02/06/2018 | 36 | In Progress | Ganesh Prabhu, Guillaume THOMAS
Host Packet Capture Analyzer tool on Eng Inf | 02/06/2018 | 36 | In Progress | Ganesh Prabhu, Guillaume THOMAS | 03/31/2018 | 03/31/2018
Host Packet Capture Analyzer tool on Eng Inf. | 02/06/2018 | 36 | In Progress | Ganesh Prabhu, Guillaume THOMAS | 03/31/2018 | 03/31/2018
DataIQ 1.5 | 02/06/2018 | 36 | In Progress | Ethan Madden, Guillaume THOMAS | 03/09/2018 | 03/09/2018
Coverity Low on Disk Space - 96% - Critical Bug | 02/06/2018 | 37 | Finished As Planned | Rick Ludvigsen, Guillaume THOMAS
Artifactory Production Upgrade & Resource Tuning | 02/05/2018 | 37 | Approved | Wade Naveja, Guillaume THOMAS
ServiceNow / Taskmaster Integration | 02/03/2018 | 40 | Scoping | Daniel Gonzalez, Stuart Higgins
Code Coverage weekly report | 02/02/2018 | 40 | New Requests | Ananthan Pillai
Code Coverage for NJ | 02/02/2018 | 40 | New Requests | Ananthan Pillai
Code Coverage : Improvements for isi_coverage.sh | 02/02/2018 | 40 | In Progress | Ananthan Pillai | 03/30/2018 | 03/30/2018
Evaluate vRealize Automation for internal cloud use | 02/02/2018 | 41 | Scoping | Daniel Mills, Guillaume THOMAS
vSphere 6.5 Upgrade | 02/02/2018 | 41 | In Progress | Daniel Mills, Guillaume THOMAS | 05/31/2018 | 05/31/2018
Deployment of Build Artifact Changes for Bug 196150 | 02/02/2018 | 41 | Finished As Planned | Rick Ludvigsen, Guillaume THOMAS
Deployment of Build Executor Version 258 | 02/02/2018 | 41 | Finished As Planned | Rick Ludvigsen, Guillaume THOMAS
Corruption Tool | 01/30/2018 | 43 | Scoping | Brooks Kindle, Guillaume THOMAS
Ability to pre-install matching customer patches on cluster pre-mechanics testing | 01/30/2018 | 44 | New Requests | Chris Tabor, Guillaume THOMAS
Replace and decommission patch upload | 01/30/2018 | 44 | New Requests | Chris Tabor, Guillaume THOMAS
Reviewboard ship-it verification & auto-updates | 01/30/2018 | 44 | New Requests | Chris Tabor, Guillaume THOMAS
Comprehensive DEBUG patch handling | 01/30/2018 | 44 | New Requests | Chris Tabor, Guillaume THOMAS
Functional script verification & testing integration | 01/30/2018 | 44 | New Requests | Chris Tabor, Guillaume THOMAS
Removal of XML preview/usage from spog and inputs | 01/30/2018 | 44 | New Requests | Chris Tabor, Guillaume THOMAS
Formal mapping of ignored files for correlation | 01/30/2018 | 44 | New Requests | Chris Tabor, Guillaume THOMAS
CloudIQ | 01/25/2018 | 48 | Scoping | Shaun Edwards, Daniel Gonzalez
MR Branch & Release Automation | 01/25/2018 | 48 | Scoping | Rick Ludvigsen, Guillaume THOMAS
Project status reporting (web server) | 01/25/2018 | 48 | In Progress | Guillaume THOMAS
Bug reports for MRs | 01/25/2018 | 48 | New Requests | Chris Tabor, Guillaume THOMAS
Leankit integration & reporting | 01/25/2018 | 48 | In Progress | Guillaume THOMAS
Quarantine Nag Mail for Leads | 01/25/2018 | 48 | Approved | Guillaume THOMAS
Incremental Build Support - DUPLICATE | 01/25/2018 | 48 | Finished As Planned | Guillaume THOMAS
OneFS Simulator Test automation | 01/25/2018 | 48 | Approved | Rick Ludvigsen, Guillaume THOMAS
Improve GitHub performance for Shanghai/India | 01/25/2018 | 48 | Scoping | Phong Truong, Guillaume THOMAS
VCenter Harmonization, Modernization and Expansion | 01/25/2018 | 48 | Scoping | Daniel Mills, Guillaume THOMAS
OneFS SysAdmin Training | 01/25/2018 | 48 | Scoping | Richard Blalock, Guillaume THOMAS
RW – Shanghai Onboarding | 01/25/2018 | 48 | Finished As Planned | Guillaume THOMAS | 02/16/2018 | 02/16/2018
RW H/W Swap & CAPEX (trading with compression team) | 01/25/2018 | 48 | Finished As Planned | Guillaume THOMAS | 02/09/2018 | 02/09/2018
Cluster N+2 project -getting CSE analysis of our cluster setup | 01/25/2018 | 48 | Scoping | Richard Blalock, Guillaume THOMAS
BugReports onboarding and Dell R-DMetrics | 01/25/2018 | 48 | In Progress | Brooks Kindle, Guillaume THOMAS | 03/12/2018 | 03/12/2018
Static Analysis for Spectre and Meltdown | 01/25/2018 | 48 | In Progress | Rick Ludvigsen, Guillaume THOMAS | 03/09/2018 | 03/23/2018 | Blocked
Code coverage support for Spectre and Meltdown | 01/25/2018 | 48 | In Progress | Rick Ludvigsen, Guillaume THOMAS
Review Board Upgrade | 01/25/2018 | 48 | Finished As Planned | Vince Thyng, Guillaume THOMAS | 02/02/2018 | 02/02/2018
Lazarus | 01/24/2018 | 49 | Finished As Planned | Evan Cramer, Daniel Gonzalez |  |  | Blocked
GCP (TEaaS) - M4 | 01/24/2018 | 49 | In Progress | Daniel Gonzalez | 06/29/2018 | 06/29/2018
GCP (TEaaS) - M3 | 01/24/2018 | 50 | In Progress | Daniel Gonzalez | 03/31/2018 | 03/31/2018
Convert existing CC scripts to Python | 01/23/2018 | 51 | Approved | Ananthan Pillai
Code Coverage for Statview | 01/09/2018 | 64 | In Progress | Ananthan Pillai | 03/30/2018 | 03/30/2018
Code Coverage for normal Python code in OneFS | 01/09/2018 | 64 | Scoping | Ananthan Pillai
CC for Python bindings | 01/09/2018 | 64 | Finished As Planned | Ananthan Pillai
Code Coverage :Dev & TestMgr Workflow | 01/09/2018 | 64 | Finished As Planned | Ananthan Pillai
Code Coverage : Incorporate WebUI CC | 01/09/2018 | 64 | New Requests | Ananthan Pillai
Code Coverage : Root Partition issue on vOneFS | 01/09/2018 | 64 | New Requests | Ananthan Pillai
Code Coverage: NDU | 01/09/2018 | 64 | New Requests | Ananthan Pillai
Code Coverage for Niijima Builds | 01/09/2018 | 64 | Finished As Planned | Ananthan Pillai
Wiki Salt automation and version upgrade | 12/13/2017 | 92 | Approved | Guillaume THOMAS, Xuan Du
Wiki Merge & Puppetize | 12/13/2017 | 92 | In Progress | Robert Haddon, Guillaume THOMAS | 02/28/2018 | 03/23/2018
Elastic (ELK) Log Stack | 12/13/2017 | 92 | Finished As Planned
Legacy Firmware Updates | 12/13/2017 | 92 | Finished As Planned
IPv6 Testing in Durham | 12/13/2017 | 92 | In Progress | Phong Truong, Guillaume THOMAS | 04/30/2018 | 04/30/2018 | Blocked
PaaS Tier 1 | 12/13/2017 | 92 | In Design | Vince Thyng, Guillaume THOMAS
Replace existing version of Puppet with SALT M1 | 12/13/2017 | 92 | Scoping | Ethan Madden, Guillaume THOMAS
Duct Tape client provisioning | 12/13/2017 | 92 | Discarded or Obsolete | Daniel Gonzalez, Tucker Siemens |  |  | Blocked
PXE Firmware upgrade via Taskmaster | 12/13/2017 | 92 | Approved | Daniel Gonzalez |  |  | Blocked
PXE firmware upgrade support | 12/13/2017 | 92 | Approved | Daniel Gonzalez
PXE Taskmaster Integration | 12/13/2017 | 92 | New Requests | Dan Forrest |  |  | Blocked
RevBot Mail Improvements | 12/13/2017 | 92 | Scoping | Dan Forrest, Daniel Gonzalez
Automated Patches M3 | 12/13/2017 | 92 | Under Review
Taskmaster Disaggregation | 12/13/2017 | 92 | Approved | Daniel Gonzalez
Automated Test Scheduler Rework | 12/13/2017 | 92 | In Progress | Daniel Gonzalez, Alba Magallanes | 03/14/2018 | 03/14/2018 | Blocked
Mandatory Test List Timeouts | 12/13/2017 | 92 | Approved | Daniel Gonzalez
Release Code Signing | 12/12/2017 | 92 | In Progress | Robert Haddon, Guillaume THOMAS |  |  | Blocked
Jenkins Upgrade | 12/12/2017 | 92 | Scoping | Rick Ludvigsen, Guillaume THOMAS
Code Coverage in Regression Wheel | 12/12/2017 | 92 | Finished As Planned | Ananthan Pillai
Code Coverage for Pipeline Builds | 12/12/2017 | 92 | In Progress | Ananthan Pillai | 03/30/2018 | 03/30/2018
Composable Release Support | 12/12/2017 | 92 | New Requests
Ice Age Integration | 12/12/2017 | 93 | Finished As Planned | Daniel Gonzalez, Alba Magallanes
Icarus Backports | 12/12/2017 | 93 | Finished As Planned | Daniel Gonzalez, Stuart Higgins | 02/23/2018 | 02/23/2018
Pull Request Automation and Management Tools | 12/12/2017 | 93 | Scoping | Brooks Kindle, Guillaume THOMAS
Migrate GHAPR to Centralized Hosting | 12/12/2017 | 93 | In Design | Vince Thyng, Guillaume THOMAS
Ongoing: Keep an eye on pcap task submissions and investigate any failures | 12/11/2017 | 94 | In Progress | Ganesh Prabhu, Guillaume THOMAS